## Dashboard
UFO Predictor · MVP2 Delivery Dashboard
MVP1 remains live while v2 is normalized onto current main, validated in stage, and delivered through bounded parallel tracks.
Total tasks | P0 tasks | Ready | In Progress | Review | Done | Blocked | Parallel tasks
45 | 24 | 2 | 0 | 1 | 0 | 0 | 23
Status | Count | Share |  | Track | Tasks
Backlog | 33 | 73.33% |  | Documentation baseline | 1
Ready | 2 | 4.444% |  | Branch normalization | 9
In Progress | 0 | 0% |  | Fixture coverage | 5
Blocked | 0 | 0% |  | Stage data foundation | 8
Review | 1 | 2.222% |  | Model release | 3
Done | 0 | 0% |  | Ops automation | 6
Deferred | 9 | 20% |  | MVP1 UI/UX | 5
|  |  |  | Internationalization | 3
|  |  |  | Commercial expansion | 2
|  |  |  | V3 research radar | 2
|  |  |  | Governance | 1

## MVP2 Backlog
ID | Epic | Track | Priority | Task | Deliverable / Description | Owner | Status | Dependencies | Base branch | Suggested branch | Environment | Parallel? | Blocks production? | Acceptance criteria | Evidence / PR | Estimate (pts) | Notes
M2-001 | M2-00 | Documentation baseline | P0 | Merge refreshed documentation and replace ChatGPT source set | Approve canonical docs, merge them, then replace uploaded sources with the exact 10-file core. | Owner | Review |  | docs/adopt-2026-06-23-project-source-refresh | docs/adopt-2026-06-23-project-source-refresh | Docs | Yes | No | Codex approves docs; docs-only diff; PR merged; source set replaced. |  | 2 | Do not upload old and new canonical files together.
M2-002 | M2-01 | Branch normalization | P0 | Audit the nine v2-only commits | Map each commit/file to data, migration, model, scripts, tests, artifacts, stale frontend, or stale docs. | Model/Data owner | Ready | M2-001 | main | audit/v2-nine-commit-preservation | Local | No | No | Preservation matrix covers every v2-only commit and file. |  | 3 | Old branch and PR #106 remain unchanged.
M2-003 | M2-01 | Branch normalization | P0 | Create current-main v2 integration branch | Create integration/prediction-intelligence-v2 from latest clean origin/main after docs merge. | Model/Data owner | Backlog | M2-001 | main | integration/prediction-intelligence-v2 | Local | No | No | Recorded base SHA equals current origin/main. |  | 1 | Do not branch from stale v2.
M2-004 | M2-01 | Branch normalization | P0 | Create parallel worktrees | Use separate main, v2 integration, and optional UI worktrees with independent ignored env files. | Model/Data owner | Backlog | M2-003 | main | ops/v2-worktree-setup | Local | Yes | No | Worktrees inspect independently; no secrets committed. |  | 1 | Use documented paths.
M2-005 | M2-01 | Branch normalization | P0 | Port migration, types, and contracts | Selectively recover migration 0038, typings, contracts, and tests onto integration branch. | Model/Data owner | Backlog | M2-002,M2-003 | integration/prediction-intelligence-v2 | feature/v2-port-schema-contracts | Local | No | No | Focused tests, lint, build, diff-check pass; no stale frontend imported. |  | 4 | Port by concern.
M2-006 | M2-01 | Branch normalization | P0 | Port source preparation and normalized data assets | Recover manifests, parsers, snapshots, aliases, schedule, venue, Elo, and FIFA assets. | Model/Data owner | Backlog | M2-005 | integration/prediction-intelligence-v2 | feature/v2-port-data-foundation | Local | No | No | Coverage counts and lineage match expected reports. |  | 5 | Use committed and external prepared-v2 assets.
M2-007 | M2-01 | Branch normalization | P0 | Port model, replay, and calibration tooling | Recover challenger, gating, replay, holdout, calibration, release candidate, and tests. | Model/Data owner | Backlog | M2-006 | integration/prediction-intelligence-v2 | feature/v2-port-model-runtime | Local | No | No | Task 2 artifacts regenerate and parity remains explainable. |  | 6 | No accuracy breakthrough claim.
M2-008 | M2-01 | Branch normalization | P0 | Port Task 3A planners and Task 3B runbook | Recover target guards and migration/import/signal/publication/export planners. | Model/Data owner | Backlog | M2-007 | integration/prediction-intelligence-v2 | feature/v2-port-ops-layer | Local | No | No | Task 3A passes on current main contracts and denies production writes. |  | 4 | Dry-run is not remote execution.
M2-009 | M2-01 | Branch normalization | P0 | Open replacement Draft PR | Open new Draft PR from integration branch after preservation/regression proof. | Model/Data owner | Backlog | M2-008 | integration/prediction-intelligence-v2 | integration/prediction-intelligence-v2 | GitHub | No | No | Draft PR includes preservation matrix and validation evidence. |  | 1 | Keep #106 Draft until proof.
M2-010 | M2-01 | Branch normalization | P1 | Mark PR #106 superseded | After replacement PR proves preservation, cross-link and close/supersede old Draft PR. | Owner | Deferred | M2-009 | integration/prediction-intelligence-v2 | docs/supersede-pr106 | GitHub | No | No | No required code/artifact lost; cross-links added. |  | 1 | Do not do early.
M2-011 | M2-02 | Fixture coverage | P0 | Discover all remaining group-stage fixture IDs | Query full remaining group stage instead of one-by-one ID discovery. | Ops owner | Ready | M2-001 | main | ops/remaining-group-stage-fixture-discovery | Production-safe read | Yes | No | Manifest has every remaining match, fixture ID, kickoff UTC, teams, group, status. |  | 3 | Can proceed with v1.
M2-012 | M2-02 | Fixture coverage | P0 | Reconcile provider fixtures with official schedule | Link API-Football fixtures to official schedule and canonical teams. | Ops owner | Backlog | M2-011 | main | ops/official-provider-fixture-linking | Local/Production-safe | Yes | No | No duplicate/unresolved group-stage links; exceptions reported. |  | 4 | Knockout placeholders may remain unresolved.
M2-013 | M2-02 | Fixture coverage | P0 | Persist canonical fixture/provider links | Store remaining fixtures and links with bounded idempotent writes. | Ops owner | Backlog | M2-012 | main | ops/persist-remaining-world-cup-fixtures | Production | Yes | Yes | Dry-run/apply match; rerun creates zero duplicates. |  | 4 | Exact target guard required.
M2-014 | M2-02 | Fixture coverage | P0 | Publish next fixture batch with current model | Generate, review, and publish upcoming predictions so coverage does not wait for v2. | Prediction Ops | Backlog | M2-013 | main | ops/publish-next-world-cup-batch | Production | Yes | Yes | Chosen not-started fixtures have immutable public predictions and detail pages. |  | 5 | Later v2 versions only before kickoff.
M2-015 | M2-02 | Fixture coverage | P1 | Maintain not-started eligibility manifest | Track fixtures eligible for a v2 version without touching started matches. | Prediction Ops | Backlog | M2-013 | main | ops/not-started-eligibility-manifest | Production-safe read | Yes | No | Manifest excludes live/finished and records cutoff/version lineage. |  | 2 | Shared by continuity and stage tests.
M2-016 | M2-03 | Stage data foundation | P0 | Run Task 3B read-only stage audit | Inspect stage migrations, schema, RLS, functions, data, source workspace, and drift. | Model/Data owner | Backlog | M2-009 | integration/prediction-intelligence-v2 | audit/task3b-stage-readonly | Stage read-only | No | No | Ordered non-destructive plan; no mutation; production target denied. |  | 4 | Stop for human approval.
M2-017 | M2-03 | Stage data foundation | P0 | Reconcile canonical migration chain in stage | Apply only approved missing canonical migrations. | Model/Data owner | Backlog | M2-016 | integration/prediction-intelligence-v2 | feature/task3b-stage-migration-sync | Stage | No | No | Migration history/schema match plan; stage Auth preserved. |  | 4 | Stage only.
M2-018 | M2-03 | Stage data foundation | P0 | Apply migration 0038 in stage | Create v2 analytical tables, indexes, constraints, and RLS. | Model/Data owner | Backlog | M2-017 | integration/prediction-intelligence-v2 | feature/task3b-apply-0038 | Stage | No | No | Migration succeeds and no-direct-read policies validate. |  | 3 | Never production during Task 3B.
M2-019 | M2-03 | Stage data foundation | P0 | Import normalized reference and historical data | Load non-sensitive prepared-v2 datasets idempotently. | Model/Data owner | Backlog | M2-018 | integration/prediction-intelligence-v2 | feature/task3b-stage-import | Stage | No | No | Counts, links, checksums, lineage match manifests. |  | 6 | No users/payments/entitlements.
M2-020 | M2-03 | Stage data foundation | P0 | Prove import idempotency | Rerun import and prove no duplicate/conflicting rows. | Model/Data owner | Backlog | M2-019 | integration/prediction-intelligence-v2 | test/task3b-import-idempotency | Stage | No | No | Second run has zero unintended inserts and stable counts. |  | 2 | Required before archive.
M2-021 | M2-03 | Stage data foundation | P0 | Persist signal snapshots | Persist cutoff, provenance, reliability, and coverage for stage fixtures. | Model/Data owner | Backlog | M2-020 | integration/prediction-intelligence-v2 | feature/task3b-signal-persistence | Stage | No | No | Signals are immutable by cutoff and RLS-safe. |  | 5 | Weak/late signals handled honestly.
M2-022 | M2-03 | Stage data foundation | P0 | Create immutable development prediction versions | Generate v2 versions only for not-started fixtures with lineage. | Model/Data owner | Backlog | M2-021,M2-015 | integration/prediction-intelligence-v2 | feature/task3b-dev-predictions | Stage | No | No | Started fixtures rejected; versions immutable; rerun idempotent. |  | 5 | No production publication.
M2-023 | M2-03 | Stage data foundation | P0 | Validate RLS, localization, venues, and stage UI | Validate public/admin projections and Spanish presentation. | Model/Data owner | Backlog | M2-022 | integration/prediction-intelligence-v2 | test/task3b-stage-product-validation | Stage | No | No | No protected leakage; aliases, venues, localization render correctly. |  | 5 | Stage Auth remains functional.
M2-024 | M2-04 | Model release | P0 | Run controlled v1/v2 stage comparison | Compare v1 and gated v2 with identical fixtures, cutoffs, and data availability. | Model owner | Backlog | M2-023 | integration/prediction-intelligence-v2 | experiment/v1-v2-stage-comparison | Stage | No | No | Metrics, scenarios, evidence, missing signals, regressions documented. |  | 5 | No tiny-holdout marketing.
M2-025 | M2-04 | Model release | P0 | Choose production release mode | Select v1 probability + v2 analysis or gated v2 probability + v2 analysis. | Owner + Model owner | Backlog | M2-024 | integration/prediction-intelligence-v2 | docs/v2-release-decision | Stage | No | No | Decision records metrics, tradeoffs, rollout, rollback, proprietary boundary. |  | 2 | Human owner decision.
M2-026 | M2-04 | Model release | P0 | Prepare production promotion plan | Define migration, data load, rollback, cutoff, and regression plan. | Model/Data owner | Backlog | M2-025 | integration/prediction-intelligence-v2 | release/v2-production-promotion-plan | Stage/Production plan | No | Yes | Owner-approved plan proves no commercial/public/admin regression. |  | 4 | No production write yet.
M2-027 | M2-05 | Ops automation | P1 | Build batch fixture discovery command | Reusable command/report for competition/date/official-manifest discovery. | Parallel engineer | Backlog | M2-011 | main | feature/ops-batch-fixture-discovery | Production-safe read | Yes | No | One run outputs IDs and DB/link state without writes. |  | 4 | Independent of v2.
M2-028 | M2-05 | Ops automation | P1 | Build bounded status/result refresh | Refresh relevant fixtures and ingest terminal results to pending_review. | Parallel engineer | Backlog | M2-027 | main | feature/ops-bounded-result-refresh | Production | Yes | Yes | Dry-run/report/apply; idempotent rerun; no auto-verification. |  | 6 | No broad silent apply.
M2-029 | M2-05 | Ops automation | P1 | Schedule once/twice-daily refresh | Run bounded refresh with retries and target guards. | Parallel engineer | Backlog | M2-028 | main | feature/ops-scheduled-fixture-refresh | Production | Yes | Yes | Scheduled runs log success/failure and do not duplicate. |  | 5 | Extra runs around dense windows.
M2-030 | M2-05 | Ops automation | P1 | Add operator notifications and run logs | Surface pending review/evaluation counts and failures without secrets. | Parallel engineer | Backlog | M2-028 | main | feature/ops-run-logging-notifications | Production | Yes | No | Actionable summary includes run ID, counts, retry guidance. |  | 4 | No raw sensitive payloads.
M2-031 | M2-05 | Ops automation | P1 | Add bounded batch evaluation persistence | Allow selected verified rows to persist evaluations in one controlled action. | Parallel engineer | Backlog | M2-030 | main | feature/ops-batch-evaluation-persistence | Production | Yes | No | Rows persist once; failures report; queue counts update. |  | 5 | Human verification already completed.
M2-032 | M2-05 | Ops automation | P2 | Automate recurring signal refresh | After v2 stage stabilization, refresh approved pre-match signals and versions. | Model/Data owner | Deferred | M2-023,M2-029 | integration/prediction-intelligence-v2 | feature/v2-recurring-signal-refresh | Stage | No | No | Cutoff/provenance preserved; started fixtures rejected. |  | 6 | Not required before Task 3B exit.
M2-033 | M2-06 | MVP1 UI/UX | P1 | Mobile and accessibility polish | Improve focus, contrast, tap targets, responsive layout, and key flows. | Parallel engineer | Backlog | M2-001 | main | feature/mvp1-mobile-accessibility-polish | Production | Yes | No | Focused tests and mobile smoke pass; no model contract change. |  | 5 | Independent microrelease.
M2-034 | M2-06 | MVP1 UI/UX | P1 | Improve loading, empty, and error states | Clarify public/admin states and reduce ambiguous technical copy. | Parallel engineer | Backlog | M2-001 | main | feature/mvp1-ui-states-polish | Production | Yes | No | No dead ends; errors actionable and safe. |  | 4 | Independent microrelease.
M2-035 | M2-06 | MVP1 UI/UX | P2 | Refine visual hierarchy and UFO/football character | Use restrained motion, blur, glow, spacing, and cards without broad redesign. | Parallel engineer | Backlog | M2-001 | main | feature/mvp1-visual-polish | Production | Yes | No | Readable, performant, tier-consistent screens. |  | 4 | No architecture rewrite.
M2-036 | M2-06 | MVP1 UI/UX | P2 | Improve admin queue ergonomics | Reduce repetitive clicks and clarify batch/empty states. | Parallel engineer | Backlog | M2-001 | main | feature/admin-ops-ux-polish | Production | Yes | No | Routine ops work does not require Real Fixture Lab. |  | 4 | Do not weaken guards.
M2-037 | M2-06 | MVP1 UI/UX | P2 | Add conversion and CTA measurement | Measure registration, pricing, checkout start, and upgrade journeys. | Parallel engineer | Backlog | M2-001 | main | feature/commercial-conversion-analytics | Production | Yes | No | Privacy-safe events distinguish anonymous/free/premium paths. |  | 4 | Owner approves provider.
M2-038 | M2-07 | Internationalization | P2 | Design locale-neutral i18n architecture | Extract keys and define locale routing/fallback without full translation. | Frontend owner | Deferred | M2-026 | main | feature/i18n-foundation | Production | Yes | No | Spanish default; canonical entities locale-neutral; routes stable. |  | 5 | Start after v2 merge.
M2-039 | M2-07 | Internationalization | P2 | Add English public/product copy | Translate core public, pricing, Auth, dashboard, and transparency surfaces. | Frontend owner | Deferred | M2-038 | main | feature/i18n-english | Production | Yes | No | English/Spanish smoke tests pass with equivalent meaning. |  | 6 | Portuguese later.
M2-040 | M2-07 | Internationalization | P2 | Add Spanish regression and fallback tests | Protect Spanish while English is introduced. | Frontend owner | Deferred | M2-039 | main | test/i18n-spanish-regression | Production | Yes | No | Missing keys fall back safely; no mixed critical flow. |  | 3 | Required before English release.
M2-041 | M2-08 | Commercial expansion | P3 | Define provider-neutral payment adapter ADR | Document product/payment/webhook/refund/revocation/reconciliation contracts. | Owner + Backend | Deferred | M2-026 | main | docs/payment-provider-adapter-adr | Docs | Yes | No | ADR preserves Wompi authority and duplicate prevention. |  | 3 | Not immediate blocker.
M2-042 | M2-08 | Commercial expansion | P3 | Evaluate PayPal Business | Assess fees, countries, UX, webhooks, refunds, disputes, and settlement. | Owner | Deferred | M2-041 | main | research/paypal-business | Research | Yes | No | Written go/no-go against Wompi and alternatives. |  | 3 | Hotmart is a channel decision.
M2-043 | M2-09 | V3 research radar | P3 | Research lineup and star-absence signals | Define sources, cutoff, reliability, anti-leakage for lineups/injuries/suspensions. | Model/Data owner | Deferred | M2-026 | integration/prediction-intelligence-v2 | research/v3-lineup-availability-signals | Research/Stage | No | No | Research memo/source contract; no production claim. |  | 5 | Potential v3 input.
M2-044 | M2-09 | V3 research radar | P3 | Research qualification-pressure and rotation context | Model final-group need, table scenarios, rotation, rest, and travel. | Model/Data owner | Deferred | M2-026 | integration/prediction-intelligence-v2 | research/v3-tournament-context | Research/Stage | No | No | Feature contract avoids subjective leakage and records cutoff. |  | 5 | Potential v3 input.
M2-045 | M2-09 | Governance | P2 | Owner decision on terms, privacy, and legal pages | Record required pages/timing before broader commercial scaling and i18n. | Owner | Backlog | M2-001 | main | docs/legal-commercial-decision | Docs | Yes | No | Decision names required pages, owner, timing, review. |  | 2 | Owner-level decision.

## Branches & Environments
Workspace / Branch | Purpose | Base | Deploy target | Database | Writes allowed | Rules
main | Production baseline and short MVP1 releases | origin/main | ufopredictor.com | Production Supabase | Production via reviewed PR/deploy | No v2 migration dependency; keep MVP1 sellable.
integration/prediction-intelligence-v2 | Normalized v2 integration | current origin/main | stage.ufopredictor.com | Stage Supabase | Stage only after audit/approval | Selective port of nine commits; replacement Draft PR.
feature/prediction-intelligence-v2-data-foundation | Historical v2 preservation branch | merge base 1dca9bf | None | None | No new implementation | Keep PR #106 Draft until supersession proof.
docs/adopt-2026-06-23-project-source-refresh | Canonical documentation refresh | origin/main e019160 | None | None | Docs only | No app code, migrations, environments, or secrets.
D:\Projects\ufo-predictor | Main worktree | main | Production | Production env file | According to task | Keep clean for production operations.
D:\Projects\ufo-predictor-v2 | V2 worktree | integration branch | Stage | Stage env file | Stage only | Independent ignored .env.local.
D:\Projects\ufo-predictor-ui | UI/UX worktree | current main | Production after PR | Production-compatible | UI only | No v2 analytical-table dependency.

## Ops Automation
Process | Current MVP1 | MVP2 increment | Target cadence | Human gate | Environment | Acceptance evidence
Fixture ID discovery | Manual date/match queries | Batch discovery manifest for remaining group stage | Ahead of publication windows | Review unresolved aliases/links | Production-safe read | Complete fixture ID/teams/kickoff/group/provider manifest
Fixture persistence | Exact guarded commands | Manifest-driven idempotent apply | As schedule expands | Approve production apply | Production | Dry-run/apply parity and zero-duplicate rerun
Status refresh | Manual exact read/apply | Relevant-fixture bounded refresh command | 1-2 times daily | No extra approval when guarded | Production | Run log, counts, retries, no broad writes
Terminal score ingest | Manual finished-fixture apply | Poll stored fixtures and create pending_review rows | 1-2 times daily / after match windows | Verification remains human | Production | No unverified public final score
Result verification | Manual admin queue | Keep human verification in initial MVP2 | 1-2 times daily | Mandatory | Production | Verified rows and audit trail
Evaluation persistence | One-by-one admin action | Bounded selected batch persistence | After verification batch | Operator selects rows | Production | Idempotent evaluations and queue counts
Signal refresh | Manual task artifacts | Recurring pre-match signal snapshot process | After v2 stage stabilization | Approve fixture/cutoff scope | Stage first | Provenance, reliability, cutoff, no started fixtures
Prediction publication | Operator review/publication | Immutable versioned not-started publication | Per fixture batch | Human review before public | Stage then Production | Version lineage and cutoff proof
Notifications | Manual page checks | Admin summary for pending review/evaluation and failures | Each scheduled run | Operator triage | Production | Actionable run ID/count/error summary

## Decisions
Decision ID | Topic | Status | Decision / question | Owner | Due gate | Notes
D-001 | V2 branch base | Decided | Create integration/prediction-intelligence-v2 from current main; preserve old branch/PR #106. | Owner + Model/Data | Before Task 3B | No blanket merge/cherry-pick.
D-002 | V2 probability mode | Open | v1 probability + v2 analysis vs gated v2 probability + v2 analysis. | Owner + Model | After stage comparison | Evidence-based release decision.
D-003 | Result verification automation | Decided for initial MVP2 | Human verification remains mandatory; automation stops at pending_review. | Owner + Ops | Before scheduler release | Revisit only with governance/reconciliation proof.
D-004 | Stage environment | Decided | Use existing stage.ufopredictor.com and separate Supabase stage. | Owner | Now | No second environment; no Docker dependency.
D-005 | Internationalization order | Decided | English after v2 stabilization and merge; Portuguese later. | Owner + Frontend | After v2 promotion | Keep canonical entities locale-neutral now.
D-006 | Second payment provider | Deferred | Evaluate PayPal Business after core v2 stabilization; Hotmart only as strategic channel. | Owner | Post-MVP2 core | Not a release blocker.
D-007 | Source workspace retention | Decided | Keep prepared-v2 external workspace until stage import/checksum/idempotency proof. | Owner + Data | Task 3B exit | Do not commit raw local source material.
D-008 | Legal pages | Open | Define required terms/privacy/legal publication timing for broader scaling. | Owner | Before broader marketing/i18n | Owner-level decision.
D-009 | V3 contextual signals | Deferred | Research lineups, absences, qualification pressure, rest/travel, and timestamped news. | Model/Data | After v2 stable | No post-kickoff leakage.

## V2 Source Registry
Asset / Path | Type | Tracked in Git? | Current role | Retention / exit rule | Verification status
D:\Projects\ufo-predictor-source-snapshots\2026-06-20\prepared-v2 | External prepared workspace | No | Raw/prepared contracts, normalized snapshots, parsing, reference, reports, source registry | Keep until stage import, checksum/lineage, and idempotency pass | Operator confirms path exists
data/prediction-engine/national-team-signals/2026-06-19/ | Committed prepared signals | Yes | Deterministic source, manifest, quality, coherence, localization outputs | Long-lived versioned source package | Present on old v2 branch
artifacts/prediction-intelligence-v2/task1...task3a/ | Committed/generated artifacts | Yes | Coverage, replay, calibration, candidate, and planner evidence | Retain as audit evidence | Present on old v2 branch
lib/prediction-intelligence-v2/ | Source code | Yes | Task libraries for data, replay, model, and planning | Selectively port to integration branch | Present on old v2 branch
scripts/prediction-intelligence-v2/ | Runnable wrappers | Yes | Task 1 through Task 3A entry points | Selectively port and reconcile paths | Present on old v2 branch
supabase/migrations/0038_prediction_intelligence_v2_data_foundation.sql | Migration | Yes | Stage analytical schema/data foundation | Apply stage only after audit/approval | Present on old v2 branch
types/database.ts | Types | Yes | Analytical table typings | Port with migration and validate current main | Present on old v2 branch

## Legacy Backlog
ID | Epic ID | Épica | Prioridad | Tarea | Descripción | Owner | Estado | Dependencias | Rama sugerida | Área | Estimación | Inicio | Límite | Notas | Progreso
T-001 | E01 | Supabase schema | P0 | Crear proyecto Supabase dev/staging | Configurar proyecto, variables y acceso del equipo sin subir secretos. | Sin asignar | Backlog |  | feature/supabase-schema | DB | 2 |  |  |  | 0%
T-002 | E01 | Supabase schema | P0 | Crear migraciones base | Tablas para usuarios, planes, fútbol, predicciones, workers y emails. | Sin asignar | Backlog |  | feature/supabase-schema | DB | 5 |  |  |  | 0%
T-003 | E01 | Supabase schema | P0 | Crear seed mínimo | Datos iniciales para probar: competiciones, equipos, partidos, planes y model version. | Sin asignar | Backlog |  | feature/supabase-schema | DB | 3 |  |  |  | 0%
T-004 | E01 | Supabase schema | P0 | Alinear types/database.ts | Actualizar tipos internos según el schema real. | Sin asignar | Backlog |  | feature/supabase-schema | Backend | 3 |  |  |  | 0%
T-005 | E01 | Supabase schema | P0 | Documentar setup Supabase | Pasos para correr migraciones y seeds local/staging. | Sin asignar | Backlog |  | feature/supabase-schema | Docs | 2 |  |  |  | 0%
T-006 | E01 | Supabase schema | P1 | Definir estrategia RLS inicial | Borrador de políticas por profiles, subscriptions, entitlements y admin. | Sin asignar | Backlog |  | feature/supabase-schema | DB | 3 |  |  |  | 0%
T-007 | E02 | Auth y roles | P0 | Configurar Supabase Auth | Email/password o proveedor elegido para registro/login. | Sin asignar | Backlog | E01 | feature/auth-roles | Auth | 3 |  |  |  | 0%
T-008 | E02 | Auth y roles | P0 | Crear flujo login/register | Pantallas o componentes mínimos para autenticación. | Sin asignar | Backlog | E01 | feature/auth-roles | Frontend | 3 |  |  |  | 0%
T-009 | E02 | Auth y roles | P0 | Crear profiles al registrarse | Hook/trigger o lógica server para perfil extendido. | Sin asignar | Backlog | E01 | feature/auth-roles | Backend | 3 |  |  |  | 0%
T-010 | E02 | Auth y roles | P0 | Definir roles base | free_user, premium_user, admin y lectura desde server. | Sin asignar | Backlog | E01 | feature/auth-roles | Auth | 2 |  |  |  | 0%
T-011 | E02 | Auth y roles | P0 | Proteger dashboard/admin | Dashboard requiere sesión; admin requiere rol admin. | Sin asignar | Backlog | E01 | feature/auth-roles | Auth | 3 |  |  |  | 0%
T-012 | E02 | Auth y roles | P1 | Estados UX de sesión | Loading, usuario no autenticado, errores y logout. | Sin asignar | Backlog | E01 | feature/auth-roles | Frontend | 2 |  |  |  | 0%
T-013 | E03 | Planes dinámicos y paywall | P0 | Leer planes desde Supabase | Reemplazar planes mock por datos reales de plans/plan_features. | Sin asignar | Backlog | E01,E02 | feature/dynamic-plans-paywall | Backend | 3 |  |  |  | 0%
T-014 | E03 | Planes dinámicos y paywall | P0 | Implementar entitlements | Permisos por plan, fase, equipo, competición o pack. | Sin asignar | Backlog | E01,E02 | feature/dynamic-plans-paywall | Backend | 5 |  |  |  | 0%
T-015 | E03 | Planes dinámicos y paywall | P0 | Implementar match unlocks | Soporte real para 10 Match Pack y partidos desbloqueados. | Sin asignar | Backlog | E01,E02 | feature/dynamic-plans-paywall | Backend | 4 |  |  |  | 0%
T-016 | E03 | Planes dinámicos y paywall | P0 | Filtrado backend premium | No enviar datos premium al frontend sin permiso. | Sin asignar | Backlog | E01,E02 | feature/dynamic-plans-paywall | Backend | 5 |  |  |  | 0%
T-017 | E03 | Planes dinámicos y paywall | P1 | Actualizar UI de locks | Bloqueos visuales según access real, no solo mock. | Sin asignar | Backlog | E01,E02 | feature/dynamic-plans-paywall | Frontend | 3 |  |  |  | 0%
T-018 | E03 | Planes dinámicos y paywall | P1 | Auditar casos de acceso | Tests/manual QA para free, premium, admin, match pack. | Sin asignar | Backlog | E01,E02 | feature/dynamic-plans-paywall | QA | 3 |  |  |  | 0%
T-019 | E04 | Motor predictivo v0.1 | P0 | Implementar normalización | Funciones para rating, forma, ataque, defensa, mercado y contexto. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Modelo | 3 |  |  |  | 0%
T-020 | E04 | Motor predictivo v0.1 | P0 | Implementar Team Power Score | Aplicar pesos v0.1 y scores trazables. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Modelo | 3 |  |  |  | 0%
T-021 | E04 | Motor predictivo v0.1 | P0 | Implementar expected goals | Calcular xG con límites y multiplicadores documentados. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Modelo | 3 |  |  |  | 0%
T-022 | E04 | Motor predictivo v0.1 | P0 | Implementar Poisson | Matriz de marcadores 0-5 por equipo. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Modelo | 4 |  |  |  | 0%
T-023 | E04 | Motor predictivo v0.1 | P0 | Calcular mercados básicos | 1X2, OU 2.5, BTTS, marcador probable y top 3. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Modelo | 5 |  |  |  | 0%
T-024 | E04 | Motor predictivo v0.1 | P0 | Calcular confidence/risk | Scores explicables según calidad, gap, mercado, lineups y estabilidad. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Modelo | 4 |  |  |  | 0%
T-025 | E04 | Motor predictivo v0.1 | P0 | Guardar prediction_versions | Persistir predicción, mercados y metadata del modelo. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | Backend | 3 |  |  |  | 0%
T-026 | E04 | Motor predictivo v0.1 | P1 | Pruebas unitarias del motor | Casos deterministas para evitar regresiones en fórmulas. | Sin asignar | Backlog | E01 | feature/prediction-engine-v01 | QA | 4 |  |  |  | 0%
T-027 | E05 | API deportiva | P1 | Evaluar API-Football vs Sportmonks | Comparar cobertura Mundial, lineups, odds, límites, costo y docs. | Sin asignar | Backlog | E01 | feature/football-api | APIs | 3 |  |  |  | 0%
T-028 | E05 | API deportiva | P1 | Crear adapter football provider | Interfaz común para cambiar proveedor sin tocar UI. | Sin asignar | Backlog | E01 | feature/football-api | Backend | 3 |  |  |  | 0%
T-029 | E05 | API deportiva | P1 | Sync fixtures | Poblar partidos reales con external_id y estado. | Sin asignar | Backlog | E01 | feature/football-api | Workers | 4 |  |  |  | 0%
T-030 | E05 | API deportiva | P1 | Sync teams/venues | Poblar equipos, logos/banderas y sedes. | Sin asignar | Backlog | E01 | feature/football-api | Workers | 3 |  |  |  | 0%
T-031 | E05 | API deportiva | P1 | Sync results/status | Actualizar live/finished y resultados finales. | Sin asignar | Backlog | E01 | feature/football-api | Workers | 3 |  |  |  | 0%
T-032 | E05 | API deportiva | P1 | Sync lineups con fallback | Alineaciones probables/confirmadas con manejo de ausencia de datos. | Sin asignar | Backlog | E01 | feature/football-api | Workers | 4 |  |  |  | 0%
T-033 | E06 | Odds y Model vs Market | P1 | Elegir proveedor de odds | Cobertura, costo, límites y mercados disponibles. | Sin asignar | Backlog | E01,E04 | feature/odds-model-market | APIs | 2 |  |  |  | 0%
T-034 | E06 | Odds y Model vs Market | P1 | Crear adapter odds provider | Interfaz fetchOdds normalizada por match/market/bookmaker. | Sin asignar | Backlog | E01,E04 | feature/odds-model-market | Backend | 3 |  |  |  | 0%
T-035 | E06 | Odds y Model vs Market | P1 | Guardar odds snapshots | Histórico de cuotas e implied probability normalizada. | Sin asignar | Backlog | E01,E04 | feature/odds-model-market | DB | 3 |  |  |  | 0%
T-036 | E06 | Odds y Model vs Market | P1 | Calcular Model vs Market real | Edge por mercado con lenguaje no agresivo. | Sin asignar | Backlog | E01,E04 | feature/odds-model-market | Modelo | 3 |  |  |  | 0%
T-037 | E06 | Odds y Model vs Market | P1 | Fallback sin odds | Ocultar sección o mostrar mensaje claro cuando falten cuotas. | Sin asignar | Backlog | E01,E04 | feature/odds-model-market | Frontend | 2 |  |  |  | 0%
T-038 | E07 | Workers Railway | P1 | Crear runner común de workers | Wrapper con logs, errores, duración y records_processed. | Sin asignar | Backlog | E01,E04,E05 | feature/railway-workers | Workers | 4 |  |  |  | 0%
T-039 | E07 | Workers Railway | P1 | Implementar generate-prediction worker | Ejecutar motor con datos disponibles y guardar versiones. | Sin asignar | Backlog | E01,E04,E05 | feature/railway-workers | Workers | 4 |  |  |  | 0%
T-040 | E07 | Workers Railway | P1 | Implementar validate-results worker | Validar aciertos y errores cuando partidos terminen. | Sin asignar | Backlog | E01,E04,E05 | feature/railway-workers | Workers | 4 |  |  |  | 0%
T-041 | E07 | Workers Railway | P1 | Configurar crons Railway | Horarios para fixtures, odds, lineups, predicciones y validación. | Sin asignar | Backlog | E01,E04,E05 | feature/railway-workers | DevOps | 3 |  |  |  | 0%
T-042 | E07 | Workers Railway | P1 | Retries y manejo de errores | Reintentos básicos y data_quality_flags si falla proveedor. | Sin asignar | Backlog | E01,E04,E05 | feature/railway-workers | Workers | 3 |  |  |  | 0%
T-043 | E07 | Workers Railway | P1 | Mostrar worker_runs reales | Conectar Admin/Beta Lab a logs reales. | Sin asignar | Backlog | E01,E04,E05 | feature/railway-workers | Frontend | 3 |  |  |  | 0%
T-044 | E08 | Resend y emails | P1 | Configurar Resend staging | Dominio/sender, API key y variables seguras. | Sin asignar | Backlog | E02,E03,E07 | feature/resend-emails | Emails | 2 |  |  |  | 0%
T-045 | E08 | Resend y emails | P1 | Crear templates React Email | Bienvenida, compra, Golden Hour, resumen diario y vencimiento. | Sin asignar | Backlog | E02,E03,E07 | feature/resend-emails | Emails | 4 |  |  |  | 0%
T-046 | E08 | Resend y emails | P1 | Implementar send-email service | Wrapper con logs en email_events. | Sin asignar | Backlog | E02,E03,E07 | feature/resend-emails | Backend | 3 |  |  |  | 0%
T-047 | E08 | Resend y emails | P1 | Golden Hour Alert | Enviar alerta a usuarios con acceso cuando haya delta relevante. | Sin asignar | Backlog | E02,E03,E07 | feature/resend-emails | Workers | 3 |  |  |  | 0%
T-048 | E08 | Resend y emails | P2 | Resumen diario | Email opcional con partidos y señales del día. | Sin asignar | Backlog | E02,E03,E07 | feature/resend-emails | Emails | 3 |  |  |  | 0%
T-049 | E09 | Admin/Beta Lab real | P1 | Conectar Admin a Supabase | Partidos, predicciones, workers y errores reales. | Sin asignar | Backlog | E01,E02,E04,E07 | feature/admin-beta-lab-real | Frontend | 4 |  |  |  | 0%
T-050 | E09 | Admin/Beta Lab real | P1 | Acciones admin protegidas | Recalcular predicción y regenerar narrativa con auditoría. | Sin asignar | Backlog | E01,E02,E04,E07 | feature/admin-beta-lab-real | Backend | 5 |  |  |  | 0%
T-051 | E09 | Admin/Beta Lab real | P1 | Vista de errores/data quality | Mostrar fallos de proveedor, missing lineups y worker errors. | Sin asignar | Backlog | E01,E02,E04,E07 | feature/admin-beta-lab-real | Frontend | 3 |  |  |  | 0%
T-052 | E09 | Admin/Beta Lab real | P2 | Filtros admin | Filtrar por competición, estado, fecha, worker y modelo. | Sin asignar | Backlog | E01,E02,E04,E07 | feature/admin-beta-lab-real | Frontend | 2 |  |  |  | 0%
T-053 | E10 | Transparency Center real | P1 | Conectar métricas reales | Calcular accuracy por mercado desde prediction_results. | Sin asignar | Backlog | E01,E04,E05,E07 | feature/transparency-real | Backend | 4 |  |  |  | 0%
T-054 | E10 | Transparency Center real | P1 | Historial de predicciones | Tabla pública con predicción, resultado y estado. | Sin asignar | Backlog | E01,E04,E05,E07 | feature/transparency-real | Frontend | 3 |  |  |  | 0%
T-055 | E10 | Transparency Center real | P1 | Separar pre/post lineup | Comparar rendimiento antes y después de alineaciones. | Sin asignar | Backlog | E01,E04,E05,E07 | feature/transparency-real | Modelo | 3 |  |  |  | 0%
T-056 | E10 | Transparency Center real | P1 | Disclaimers y explicación | Texto claro: probabilidades, no asesoría financiera. | Sin asignar | Backlog | E01,E04,E05,E07 | feature/transparency-real | Producto | 2 |  |  |  | 0%
T-057 | E11 | UI polish y mobile | P2 | Revisión mobile real | Navbar, cards, tablas, pricing y admin en celular. | Sin asignar | Backlog |  | feature/ui-polish-mobile | Frontend | 3 |  |  |  | 0%
T-058 | E11 | UI polish y mobile | P2 | Estados loading/empty/error | Componentes para datos reales faltantes o fallos. | Sin asignar | Backlog |  | feature/ui-polish-mobile | Frontend | 3 |  |  |  | 0%
T-059 | E11 | UI polish y mobile | P2 | Accesibilidad básica | Contraste, focus, labels, navegación teclado. | Sin asignar | Backlog |  | feature/ui-polish-mobile | QA | 2 |  |  |  | 0%
T-060 | E11 | UI polish y mobile | P2 | Branding assets finales | Favicon optimizado, logos transparentes, social preview. | Sin asignar | Backlog |  | feature/ui-polish-mobile | Diseño | 3 |  |  |  | 0%
T-061 | E12 | Deploy y staging | P0 | Configurar Railway project | Build command, start command y variables base. | Sin asignar | Backlog | E01 | feature/staging-deploy | DevOps | 3 |  |  |  | 0%
T-062 | E12 | Deploy y staging | P0 | Staging deploy desde main/develop | URL estable para revisión del equipo. | Sin asignar | Backlog | E01 | feature/staging-deploy | DevOps | 3 |  |  |  | 0%
T-063 | E12 | Deploy y staging | P0 | Configurar variables seguras | Supabase, Resend, API providers y LLM sin secretos en repo. | Sin asignar | Backlog | E01 | feature/staging-deploy | DevOps | 2 |  |  |  | 0%
T-064 | E12 | Deploy y staging | P1 | Documentar flujo de deploy | README con pasos y troubleshooting. | Sin asignar | Backlog | E01 | feature/staging-deploy | Docs | 2 |  |  |  | 0%
T-065 | E12 | Deploy y staging | P1 | Smoke test de staging | Validar rutas, build, env vars y logs. | Sin asignar | Backlog | E01 | feature/staging-deploy | QA | 2 |  |  |  | 0%

## MVP1 Roadmap History
ID | Fase | Área | Épica / tarea | Estado | Resultado / objetivo | PR / Migración / rama | Notas
A01 | A — Fundación técnica | Contexto | Project context & docs foundation | Done | Fuentes iniciales, reglas de trabajo, handoffs y contexto del proyecto. | feature/project-context | Base documental inicial.
A02 | A — Fundación técnica | Frontend | Initial UFO Predictor prototype | Done | Prototipo Next.js/Tailwind con rutas principales y mock data. | feature/initial-prototype | Home, predictions, match detail, pricing, transparency, dashboard, admin.
A03 | A — Fundación técnica | DB | Initial Supabase schema | Done | Schema base, tablas iniciales y seed. | feature/supabase-schema / 0001 | Supabase remoto aplicado manualmente.
A04 | A — Fundación técnica | DB | Match season/competition integrity | Done | Integridad entre matches, seasons y competitions reforzada. | fix/supabase-schema-integrity | FK compuesta y limpieza de schema.
A05 | A — Fundación técnica | Supabase | Supabase runtime clients | Done | Clientes Supabase browser/server/admin y setup runtime. | feature/supabase-runtime-setup | Base para queries server/browser.
A06 | A — Fundación técnica | Auth | Supabase auth and role guards | Done | Email/password auth, profiles automáticos, roles free_user/admin. | feature/auth-roles | Dashboard/admin protegidos.
A07 | A — Fundación técnica | Tipos | Types and contracts alignment | Done / Iterativo | Tipos TS y contratos actualizados conforme migraciones. | types/database.ts | Sigue siendo iterativo cuando cambie DB.
A08 | A — Fundación técnica | UX | Mock plans and visual paywall | Done parcial | Planes/locks visuales iniciales en prototipo. | Prototype | Luego reemplazado por entitlements backend.
B01 | B — Lab interno pre-Mundial | Admin Lab | Beta Lab Foundation | Done | /admin/beta-lab protegido para operación interna. | feature/beta-lab-foundation | internal_lab, lab_only, run_scope.
B02 | B — Lab interno pre-Mundial | Data | Data Intake Foundation / Minimal | Done | Fixtures/resultados mínimos, fuente/calidad de datos. | feature/data-intake-minimal / 0004 | Base para validar datos pre-Mundial.
B03 | B — Lab interno pre-Mundial | Modelo | Prediction Engine v0.1 Lab | Done | Motor determinístico inicial con tests. | lib/prediction-engine | El modelo calcula; IA solo explica.
SEC01 | B — Lab interno pre-Mundial | Security | Restrict lab match results RLS | Done | RLS reforzada para resultados Lab/admin. | RLS migration | Admin-only donde aplica.
B04 | B — Lab interno pre-Mundial | Evaluación | Model Evaluation Lab | Done | Comparar predicciones contra resultados validados. | lib/model-evaluation | Tests incluidos.
B05 | B — Lab interno pre-Mundial | Supabase | Lab Supabase Queries | Done | Beta Lab lee datos reales desde Supabase. | Lab query layer | Mantiene Lab aislado de producto público.
B06a | B — Lab interno pre-Mundial | Admin Lab | Lab Fixture Review Actions | Done | Admin puede revisar fixtures. | PR #15 / 0007 | Campos review/status/calidad.
B06b | B — Lab interno pre-Mundial | Admin Lab | Lab Match Result Actions | Done | Admin puede crear/editar match_results. | PR #16 / 0008 | Resultados verificados o pendientes.
B06-pre | B — Lab interno pre-Mundial | Admin Lab | Seed Internal Lab Prediction Markets | Done | Markets internos sembrados/readables para Lab. | PR #17 / 0009 | No públicos.
B06c | B — Lab interno pre-Mundial | Evaluación | Lab Evaluation Persistence | Done | Persistir/actualizar prediction_results desde Lab. | PR #18 / 0010 | MVP interno de evaluación cerrado.
DOCS01 | B — Lab interno pre-Mundial | Docs | Update context after Lab Admin Flow | Done | Refresh documental post Lab Admin Flow. | PR #19 | Fuentes actualizadas para no rehacer B06.
C01 | C — Producto público / freemium | Public Product | Public Predictions From DB | Done | /predictions lee predicciones públicas desde Supabase. | PR #20 / 0011 | Usa public_prediction_summaries; sin premium.
C02 | C — Producto público / freemium | Access | Plans & Entitlements Backend | Done | /pricing y /dashboard leen planes/acceso reales. | PR #21 / 0012 | plans, subscriptions, user_entitlements, user_match_unlocks.
DOCS02 | C — Producto público / freemium | Docs | Update context after C02 | Done | Refresh documental post C02. | PR #22 | Actualizó baseline de planes/entitlements.
C03 | C — Producto público / freemium | Public Product | Match Detail Public From DB | Done | /matches/[slug] lee detalle público/free-only desde Supabase. | PR #23 / 0013 | public_match_details + public_prediction_summaries.
DOCS03 | C — Producto público / freemium | Docs | Update project context after C03 | Done | Refresh documental post C03. | PR #24 | Baseline para C04.
C04 | C — Producto público / freemium | Access/Security | Premium Access Enforcement Skeleton | Done | Skeleton server-side para decidir acceso premium match sin servir payload. | PR #25 | PremiumMatchResource, resolvePremiumMatchAccess, stageAccessKey, helper server-only, tests.
C05-G0 | C — Producto público / freemium | Product | Anonymous vs Registered Free Product Audit | Done / Decisión | Auditoría de brecha: anónimo y registrado free hoy ven casi lo mismo. | Reconocimiento Codex | Concluyó que hace falta value wall de registro.
C05-G1 | C — Producto público / freemium | UX/Product | Registered Free Value Wall | Current / Next | Hacer que registrarse gratis tenga valor visible sin SQL ni premium real. | Pendiente | CTAs, copy, teaser/locks seguros, dashboard free útil, pricing claro.
C05-G2 | C — Producto público / freemium | Data Boundary | Data Boundary: Anonymous vs Registered Free | Next | Decidir qué datos ve anónimo y qué datos pasan a registrado free. | Pendiente | Puede requerir nueva projection/RLS si se separa data layer.
C05-G3 | C — Producto público / freemium | User Data | Registered Free Capture Foundation | Later | Favoritos, watchlist, preferencias, eventos de uso/interés. | Pendiente | Requiere SQL/RLS si se implementa formalmente.
C06 | C — Producto público / freemium | Premium | Entitled / Premium Match Projection | Later | Servir contenido premium real solo a usuarios autorizados. | Pendiente | View/RPC/server-only query con autorización; no abrir tablas base premium.
C07 | C — Producto público / freemium | Trust | Trust / Transparency Real v0.1 | Later | Reemplazar transparency mock por métricas reales trust-eligible. | Pendiente | Definir desde qué modelo/fecha cuenta el Trust Score.
D01 | D — Datos y automatización | Data Provider | Sports API Provider Decision | Future | Elegir proveedor de fixtures/resultados. | Pendiente | Criterios: cobertura Mundial/ligas, costo, cuotas, confiabilidad.
D02 | D — Datos y automatización | Data Provider | Sports API Integration | Future | Integrar proveedor real de datos deportivos. | Pendiente | Fixture/result sync real.
D03 | D — Datos y automatización | Workers | Workers Runtime | Future | Jobs reales para sync/generación/evaluación. | Pendiente | Reemplazar workerRuns mock.
D04 | D — Datos y automatización | Workers | Automated Prediction Generation | Future | Generar predicciones automáticamente. | Pendiente | Depende de data provider/workers.
D05 | D — Datos y automatización | Evaluation | Automated Evaluation | Future | Evaluar predicciones automáticamente con resultados reales. | Pendiente | Alimenta Trust/Transparency.
E01 | E — Comercial / Premium | Product | Premium Product Definition | Future | Definir exactamente qué desbloquea premium pago. | Pendiente | Post-Mundial / cuando free funnel tenga datos.
E02 | E — Comercial / Premium | Access | Premium Plans / Packs / Unlocks | Future | Planes pagos, packs, team/competition/stage passes. | Pendiente | Pocos planes visibles, permisos internos granulares.
E03 | E — Comercial / Premium | Payments | Payments / Stripe | Future | Checkout y pagos reales. | Pendiente | No antes de validar producto/valor.
E04 | E — Comercial / Premium | Launch | Post-World-Cup Premium Launch | Future | Convertir registrados free a pago después de validar. | Pendiente | Estrategia comercial post-Mundial.
E05 | E — Comercial / Premium | Retention | Retention / Notifications | Future | Alertas, emails, notificaciones y retención. | Pendiente | Puede requerir Resend/cron.
F01 | F — IA / Explicaciones | Contracts | Narrative Contracts | Future | Definir contratos de explicación para outputs del modelo. | Pendiente | La IA explica, no calcula.
F02 | F — IA / Explicaciones | LLM | LLM Explanation Layer | Future | Narrativas generadas por IA sobre predicciones ya calculadas. | Pendiente | No fuente de probabilidades.
F03 | F — IA / Explicaciones | i18n/Narratives | Multi-language Narrative Strategy | Future | Definir si narrativas se guardan/generan/traducen por idioma. | Pendiente | No antes de servir narratives.
G01 | G — Infra / Escala | Deploy | Staging | Future | Entorno staging/QA estable. | Pendiente | Antes de beta más pública.
G02 | G — Infra / Escala | QA/Security | QA/Security Pass | Future | Revisión RLS, rutas admin, exposición accidental. | Pendiente | Crítico antes de premium/public beta amplia.
G03 | G — Infra / Escala | Observability | Observability / Logging | Future | Monitoreo técnico y errores. | Pendiente | Útil al crecer tráfico.
G04 | G — Infra / Escala | Dev Workflow | Supabase CLI Local Setup | Future | Flujo local de migraciones más sano. | Pendiente | Hoy remoto se aplica manualmente.
G05 | G — Infra / Escala | i18n | Public Site EN/ES | Future | Sitio público bilingüe inglés/español. | Pendiente | Data interna canónica preferiblemente en inglés.
G06 | G — Infra / Escala | Auth | Google Auth | Future | Reducir fricción de registro. | Pendiente | Útil cuando value wall esté claro.